## Members List
Name | Primary Role | email | Cell phone | Class01 | Class02 | Class03 | Class04 | Class05 | Work Schedule | Other Conflicts
Sam | Scrum Master | SamuelBMorris41899@gmail.com | 2052396435 | CS 499 | CS 103 | CS 347 | CS 390 | CS 443 | None | moving to Philly in May, this does not cause problems now, but may in the future.
Bryce | Team Lead | bcb0033@uah.edu | 8652303400 | CS 499 | CS 465 | CM 113 | HY 222 | #N/A | 8am - 4pm Mon-Thu, includes both work and school
Pierre |  | pmg0010@uah.edu | 2054170106 | CS 499 | CS 490 | CS 424 | CS 465 | #N/A | MWF 6am-~7pm, T,TR 8am-~6pm | HSV utilities/campus job may ask me to work some weekends, some weekends I drive home to take care of my mother
Chaz |  | cry0003@uah.edu | 2054410261 | CS 499 | CS 490 | CS 424 | PHL 403 | #N/A | Fairly open | Possibly other classes coming up

## Meetings
Member | M01 | M02 | M03 | M04 | M05 | M06 | M07 | M08 | M09 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23
Date--> | 2022-01-11 | 2022-01-13 | 2022-01-18 | 2022-01-22
Sam | Present | Absent - Unknown | Present | Present
Bryce | Present | Present | Present | Recorder
Pierre | Present | Recorder | Recorder | Present
Chaz | Present | Present | Present | Present
Meeting Minutes | Got to meet and discuss a little about the team | https://docs.google.com/document/d/1FiHYzerAfcxR32JLNc62Wz9frG3MbLFIbiTUE0AMYsA/edit?usp=sharing | https://docs.google.com/document/d/1KVeZ-sLNExO7yfVYl9eYgjYAYFhji94LiDixYNj6ZPw/edit?usp=sharing
Time (hrs) | 0.5 | 1.5 | 1 | 2.5

## Action Items
Tracking Number | Open Date | Status | Closed Date | Assigned to | Title | Action Details | Closure Details
AI-01 | 2022-01-13 | Open |  | Bryce | Begin React Training, 4.1,5.1 | Begin learning react and refresh yourself on sections 4.1 and 5.1
AI-02 | 2022-01-13 | Open |  | Pierre | Library Research, 5.2,5.4 | Consider different python libraries to aid in discrete math and resfresh yourself on sections 5.2 and 5.4
AI-03 | 2022-01-13 | Open |  | Chaz | Begin React Training, 6.1,6.2 | Begin learning react and refresh yourself on sections 6.1 and 6.2
AI-04 | 2022-01-13 | Open |  | Sam | 1.1,1.2 Research | Refresh yourself on sections 1.1 and 1.2, do preliminary code work on section 1.1
AI-05 | 2022-01-23 | Open |  | Chaz | 5.7 Research and Design | Research libraries and create algorithms for boolean matrix operations from 5.7
AI-06 | 2022-01-23 | Open |  | Pierre | Finish 5.2 and 5.4 algorithms | Finish up the algorithms and test them on all homework problems
AI-07
AI-08

## Epics
Epic ID | Short Title | Description
E01.1.1 | Section 1.1 Problems | As a User, I want to be able to enter Problems from Section 1.1 so that I can see their solutions and a step-by-step guide to solving them.
E01.1.2 | Section 1.1 Examples | As a User, I want to be able to review Problems from Section 1.1 so that I can see their solutions and a step-by-step guide to solving them.
E01.2.1 | Section 1.2 Problems | As a User, I want to be able to enter Problems from Section 1.2 so that I can see their solutions and a step-by-step guide to solving them.
E01.2.2 | Section 1.2 Examples | As a User, I want to be able to review Problems from Section 1.2 so that I can see their solutions and a step-by-step guide to solving them.
E03.1.1 | Section 3.1 Problems | As a User, I want to be able to enter Problems from Section 3.1 so that I can see their solutions and a step-by-step guide to solving them.
E03.1.2 | Section 3.1 Examples | As a User, I want to be able to review Problems from Section 3.1 so that I can see their solutions and a step-by-step guide to solving them.
E04.1.1 | Section 4.1 Problems | As a User, I want to be able to enter Problems from Section 4.1 so that I can see their solutions and a step-by-step guide to solving them.
E04.1.2 | Section 4.1 Examples | As a User, I want to be able to review Problems from Section 4.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.1.1 | Section 5.1 Problems | As a User, I want to be able to enter Problems from Section 5.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.1.2 | Section 5.1 Examples | As a User, I want to be able to review Problems from Section 5.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.2.1 | Section 5.2 Problems | As a User, I want to be abe to enter Problems from section 5.2 so that I can see their solutions and a step-by-step guide to solving them.
E05.2.2 | Section 5.2 Examples | As a User, I want to be able to review Problems from section 5.2 so that I can see their solution and a step-by-step guide to solving them
E05.4.1 | Section 5.4 Problems | As a User, I want to be able to enter Problems from Section 5.4 so that I can see their solutions and a step-by-step guide to solving them.
E05.4.2 | Section 5.4 Examples | As a User, I want to be able to review Problems from Section 5.4 so that I can see their solutions and a step-by-step guide to solving them.
E05.5.1 | Section 5.5 Problems | As a User, I want to be able to enter Problems from Section 5.5 so that I can see their solutions and a step-by-step guide to solving them.
E05.5.2 | Section 5.5 Examples | As a User, I want to be able to review Problems from Section 5.5 so that I can see their solutions and a step-by-step guide to solving them.
E05.7.1 | Section 5.7 Problems | As a User, I want to be able to enter Problems from Section 5.7 so that I can see their solutions and a step-by-step guide to solving them.
E05.7.2 | Section 5.7 Examples | As a User, I want to be able to review Problems from Section 5.7 so that I can see their solutions and a step-by-step guide to solving them.
E06.1.1 | Section 6.1 Problems | As a User, I want to be able to enter Problems from Section 6.1 so that I can see their solutions and a step-by-step guide to solving them.
E06.1.2 | Section 6.1 Examples | As a User, I want to be able to review Problems from Section 6.1 so that I can see their solutions and a step-by-step guide to solving them.
E06.2.1 | Section 6.2 Problems | As a User, I want to be able to enter Problems from Section 6.2 so that I can see their solutions and a step-by-step guide to solving them.
E06.2.2 | Section 6.2 Examples | As a User, I want to be able to review Problems from Section 6.2 so that I can see their solutions and a step-by-step guide to solving them.
E07.1.1 | Section 7.1 Problems | As a User, I want to be able to enter Problems from Section 7.1 so that I can see their solutions and a step-by-step guide to solving them.
E07.1.2 | Section 7.1 Examples | As a User, I want to be able to review Problems from Section 7.1 so that I can see their solutions and a step-by-step guide to solving them.
E08.1 | Website User Input | As a User, I want to be able to manually enter logical problems so that I can better study CS 214 and check my work.
E08.2 | Website Bug Reporting | As a User, I want to be able to report problems with the site to the webmaster.
E09.1 | Webmaster Controls | As a Webmaster, I want to be able to review user data such as basic user information, connection time, features used/accessed, and user inputs so that I can monitor website usage.

## User Stories
Parent Epic ID | User Story ID | Title | Description | Assigned to - Primary | Assigned to - Secondary | Sprint Number
E01.1.1 | US01 | Truth Table Construction | Construct Truth Table from wff. Note any tautologies or contradictions. | Sam |  | 1
E01.1.1 | US02 | Tautological Proofing | Convert left side of bioconditional statement to right side in order to verify a tautology. Step-by-step justification required. | Sam |  | 1
E01.1.2 | US03 | Section 1.1 Web-Examples | Lay out practice and example problems from Section 1.1 on web
E01.2.1 | US04 | Justify Proofing Sequence | Jusitfy propositional logic proofing sequence with steps
E01.2.2 | US05 | Section 1.2 Web-Examples | Lay out practice and example problems from Section 1.2 on web
E03.1.1 | US06 | Section 3.1 Recursive Defintions | Be able to solve 3.1 homework problems on web | Sam
E03.1.2 | US07 | Section 3.1 Web-Examples | Lay out practice and example problems from Section 3.1 on web | Sam
E04.1.1 | US08 | Is statement true given Set definition | User input set definition either in form {x,y,z,...} or {x¦x ∈ N and 1 < x < 50}, tell whether 5 ⊆ A is true or false and why or why not.
E04.1.1 | US09 | Power Set Computation | Compute and display the power set given a user-entered set. Nested power sets must be able to be worked as well.
E04.1.1 | US10 | Homework Problem 40b | Is given operation a binary operations on set S?
E04.1.1 | US11 | Set Operations (Union, Intersect, Compliment, Subsets, Difference, Cross Product) | Homework problems 47 - 51.
E04.1.2 | US12 | Section 4.1 Web-Examples | Lay out practice and example problems from 4.1 on web.
E05.1.1 | US13 | Test Binary relations on S for reflexivity, symmetry, antisymmetry, and transitivity | Problems 11 and 12 from Section 5.1
E05.1.1 | US14 | Find reflexiv, symmetric, and transitive closures given sets and relations | Problems 23 and 24 from Section 5.1
E05.1.1 | US15 | Draw Hasse Diagrams for Partial Orderings | Problem 31 from Section 5.1
E05.1.1 | US16 | for problem 31 name least, minimal, greatest, and max elements | Problem 32 from Section 5.1
E05.1.1 | US17 | partitions, list ordered pairs, equivalence relation | Problem 51a and b
E05.1.2 | US18 | Section 5.1 Web-Examples | Lay out practice and example problems from 5.1 on web
E05.2.1 | US19 | Construct PERT charts, compute min time | Construct PERT charts from task table, and compute minimum time | Pierre
E05.2.1 | US20 | Create topological Sort for partially ordered set | create algo that can create a tree in an array for partially ordered sets | Pierre
E05.2.2 | US21 | Section 5.2 Web-examples | Lay out practice and example problems from 5.2 on the web | Pierre
E05.4.1 | US22 | Section 5.4 Web - Examples | Lay out practice and example problems from 5.4 on web | Pierre
E05.4.2 | US23 | Solve permutation functions in cycle form | create algo to solve and display exceptions | Pierre
E05.4.2 | US24 | composition of permutation cycles /disjoint cycles | get the composition of permuation cycles with disjoint cycles | Pierre
E05.5.1 | US25 | Prove, by finding constants, an order of magnitude problem | Problems 3-6 from Section 5.1
E05.5.1 | US26 | Use Master Theorem to determine an order of magnitude expression | Problems 21-26 from Section 5.1
E05.5.2 | US27 | Section 5.5 Web-examples | Lay out practice and example problems from 5.5 on the web.
E06.1.1 | US28 | *6.1* Create an adjacency matrix from a graph | Read edges of a graph and convert it to an adjacency matrix | Chaz
E06.1.1 | US29 | Create a graph from an adjacency matrix | Read in a matrix and convert it to an image file of a graph | Chaz
E06.1.1 | US30 | Create an adjacency list from a graph | Read edges of a graph and convert it to a list of connections | Chaz
E06.1.1 | US31 | Create a graph from an adjacency list | Read in an adjacency list and convert it to an image file of a graph | Chaz
E06.1.1 | US32 | Create array-pointer representations from a graph | Read in a graph and create a table of the array-pointer representations | Chaz
E06.1.2 | US33 | Section 6.1 Web-Examples | Lay out practice and example problems from 6.1
E06.2.1 | US34 | Section 6.2 Web - Examples | Lay out practice and example problems from 6.2
E06.2.2 | US35 | Expression trees (5-8) | be able to create expression trees from equations
E06.2.2 | US36 | left child right child representation (9-12,15,16) | write/draw left child and right child from binary trees and trees
E06.2.2 | US37 | (preorder, inorder, postorder) traversal (19-24) | write the list of nodes in all forms of traversale
E06.2.2 | US38 | prefix, postfix, infix, expression (25 - 32) | write from any notation into any other notation and evaluate them
US39
US40
US41
US42
US43
US44
US45
US46
US47
E05.7.1 | US48 | boolean matrix structure | create Structure to store boolean matrix | Chaz
E05.7.1 | US49 | boolean matrix operation | Cross Matrix, AND, OR, ETC | Chaz
E05.7.1 | US50 | boolean matrix Input and GUI solver | Render the MAtrix and show the steps taken to solve the matrix | Chaz
US51
US52
US53
US54
US55
US56
US57
US58
US59
US60
US61
US62
US63
US58
US59
US60
US61
US62
US63
US64
US65
US66
US67
US68
US69
US70
US70
US71

## Configuration Items
CI-ID | Short Name | Long description
CI-01
CI-02
CI-03
CI-04
CI-05
CI-06
CI-07
CI-08
CI-09

## Requirements
Parent CI | Requirement ID | Title | Requirement Statement (Shall) | Additonal Information | Assigned to
Rqmt01
Rqmt02
Rqmt03
Rqmt04
Rqmt05
Rqmt06
Rqmt07
Rqmt08
Rqmt09
Rqmt10
Rqmt11
Rqmt12
Rqmt13
Rqmt14
Rqmt15
Rqmt16
Rqmt17
Rqmt18
Rqmt19
Rqmt20
Rqmt21
Rqmt22
Rqmt23
Rqmt24
Rqmt25
Rqmt26
Rqmt27
Rqmt28
Rqmt29
Rqmt30
Rqmt31
Rqmt32
Rqmt33
Rqmt34

## Key Decisions
Key Decision ID
KD01 | Using python as our backend and java script with react for front end
KD02 | We are choosing to use Epics and User Stories
KD03
KD04
KD05
KD06
KD07
KD08
KD09
KD10
KD11
KD12

## Schedule
Title | Scheduled Start Date | Actual Start Date | Scheduled Complete Date | Actual Complete Date | Assigned to | Verified by
Team Report Week 1 | 2022-01-11 | 2022-01-11 | 2022-01-16 | 2022-01-16 | ALL | Bryce
Team Report Week 2 | 2022-01-17 | 2022-01-18 | 2022-01-23 |  | Bryce | Bryce
Team Report Week 3 |  |  | 2022-01-30
Team Report Week 4 |  |  | 2022-02-06
Team Report Week 5 |  |  | 2022-02-13
Team Report Week 6 |  |  | 2022-02-20
Team Report Week 7 |  |  | 2022-02-27
Team Report Week 8 |  |  | 2022-03-06
Team Report Week 9 |  |  | 2022-03-13
Team Report Week 10 |  |  | 2022-03-20
Team Report Week 11 |  |  | 2022-03-27
Team Report Week 12 |  |  | 2022-04-03
Team Report Week 13 |  |  | 2022-04-10
Team Report Week 14 |  |  | 2022-04-17
Team Report Week 15 |  |  | 2022-04-24
Team Report Week 16 |  |  | 2022-05-01
Individual Report Week 1 | 2022-01-11 | 2022-01-11 | 2022-01-16 | 2022-01-16 | ALL | ALL
Individual Report Week 2 | 2022-01-17 | 2022-01-17 | 2022-01-23 |  | ALL | ALL
Individual Report Week 3 |  |  | 2022-01-30
Individual Report Week 4 |  |  | 2022-02-06
Individual Report Week 5 |  |  | 2022-02-13
Individual Report Week 6 |  |  | 2022-02-20
Individual Report Week 7 |  |  | 2022-02-27
Individual Report Week 8 |  |  | 2022-03-06
Individual Report Week 9 |  |  | 2022-03-13
Individual Report Week 10 |  |  | 2022-03-20
Individual Report Week 11 |  |  | 2022-03-27
Individual Report Week 12 |  |  | 2022-04-03
Individual Report Week 13 |  |  | 2022-04-10
Individual Report Week 14 |  |  | 2022-04-17
Individual Report Week 15 |  |  | 2022-04-24
Individual Report Week 16 |  |  | 2022-05-01
SDP Submission |  |  | 2022-01-31
User Stories /Requirements |  |  | 2022-02-14
Architerctural Design |  |  | 2022-03-07
Preliminary GIU Design |  |  | 2022-03-28
Beta Release |  |  | 2022-03-31
Delivery Rev 1.0 |  |  | 2022-03-12
Final delivery |  |  | 2022-04-25
Formulas:
Actual Start Date = [Scheduled Start Date]
Actual Complete Date = [Scheduled Complete Date]
Scheduled Complete Date = [Scheduled Complete Date, row above]+7

## Risk Tracking
Risk ID | Risk Title | Likelihood | Impact Level | Risk Score | Mitigation Steps
R-01 |  |  |  | 0
R-02 |  |  |  | 0
R-03 |  |  |  | 0
R-04 |  |  |  | 0
R-05 |  |  |  | 0
R-06 |  |  |  | 0
R-07 |  |  |  | 0

## Test Cases
Test Case Number | Requirement(s) | Title | Description | Assigned to: | Status
TC01
TC02
TC03
TC04
TC05
TC06
TC07
TC08
TC09

## Problem Reports
Number | Title | Date Open | Status | Assigned to: | Verified by: | Date Closed
SPR-01
SPR-02
SPR-03
SPR-04
SPR-05
SPR-06
SPR-07
SPR-08
SPR-09
SPR-10
SPR-11
SPR-12
SPR-13
SPR-14
SPR-15
SPR-16
SPR-17
SPR-18
SPR-19
SPR-20
SPR-21
SPR-22
SPR-23
SPR-24
SPR-25
SPR-26
SPR-27
SPR-28
SPR-29

## Lists
Primary Role | Meeting Role | AI Status | Term Start Date | Term End Date | Test Status | SPR Status | Assignments
Team Lead | Moderator | Open | 2022-01-11 | 2022-04-29 | Not Tested | Open | Sam
Technical Lead | Recorder | Closed-Resolved |  |  | In-Process | In-Work | Bryce
Technical Writer | Present | Closed-Withdrawn |  |  | Tested-Failed | Corrected | Pierre
Test Lead | Absent - Known | Pending |  |  | Tested-Passed | Closed | Chaz
Tools Lead | Absent - Unknown
CM Lead | [6 empty] | ALL
Quality Lead | [6 empty] | TBD
Scrum Master | [6 empty] | NA