## Members List
Name | Primary Role | email | Cell phone | Class01 | Class02 | Class03 | Class04 | Class05 | Work Schedule | Other Conflicts
Sam | Scrum Master | SamuelBMorris41899@gmail.com | 2052396435 | CS 499 | CS 103 | CS 347 | CS 390 | CS 443 | None | moving to Philly in May, this does not cause problems now, but may in the future.
Bryce | Team Lead | bcb0033@uah.edu | 8652303400 | CS 499 | CS 465 | CM 113 | HY 222 | #N/A | 8am - 4pm Mon-Thu, includes both work and school
Pierre | Technical Lead | pmg0010@uah.edu | 2054170106 | CS 499 | CS 490 | CS 424 | CS 465 | #N/A | MWF 6am-~7pm, T,TR 8am-~6pm | HSV utilities/campus job may ask me to work some weekends, some weekends I drive home to take care of my mother
Chaz |  | cry0003@uah.edu | 2054410261 | CS 499 | CS 490 | CS 424 | PHL 403 | #N/A | Fairly open | Possibly other classes coming up

## Meetings
Member | M01 | M02 | M03 | M04 | M05 | M06 | M07 | M08 | M09 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23
Date--> | 2022-01-11 | 2022-01-13 | 2022-01-18 | 2022-01-22 | 2022-01-29
Sam | Present | Absent - Unknown | Present | Present | Recorder
Bryce | Present | Present | Present | Recorder | Present
Pierre | Present | Recorder | Recorder | Present | Present
Chaz | Present | Present | Present | Present | Present
Meeting Minutes | Got to meet and discuss a little about the team | https://docs.google.com/document/d/1FiHYzerAfcxR32JLNc62Wz9frG3MbLFIbiTUE0AMYsA/edit?usp=sharing | https://docs.google.com/document/d/1KVeZ-sLNExO7yfVYl9eYgjYAYFhji94LiDixYNj6ZPw/edit?usp=sharing | Meeting goal was to create user stories for the Section specific Epics | Finish SDP Document/Presenstation
Time (hrs) | 0.5 | 1.5 | 1 | 2.5 | 1.5

## Action Items
Tracking Number | Open Date | Status | Closed Date | Assigned to | Title | Action Details | Closure Details
AI-01 | 2022-01-13 | Closed-Resolved | 2022-01-22 | Bryce | Begin React Training, 4.1,5.1 | Begin learning react and refresh yourself on sections 4.1 and 5.1
AI-02 | 2022-01-13 | Closed-Resolved | 2022-01-30 | Pierre | Library Research, 5.2,5.4 | Consider different python libraries to aid in discrete math and resfresh yourself on sections 5.2 and 5.4
AI-03 | 2022-01-13 | Open |  | Chaz | Begin React Training, 6.1,6.2 | Begin learning react and refresh yourself on sections 6.1 and 6.2
AI-04 | 2022-01-13 | Open |  | Sam | 1.1,1.2 Research | Refresh yourself on sections 1.1 and 1.2, do preliminary code work on section 1.1
AI-05 | 2022-01-23 | Open |  | Chaz | 5.7 Research and Design | Research libraries and create algorithms for boolean matrix operations from 5.7
AI-06 | 2022-01-23 | Closed-Resolved | 2022-01-30 | Pierre | Finish 5.2 and 5.4 algorithms | Finish up the algorithms and test them on all homework problems
AI-07 | 2022-01-24 | Closed-Resolved | 2022-01-30 | All | SDP | Create SDP Document/Presentation
AI-08

## Epics
Epic ID | Short Title | Description
E01.1.1 | Section 1.1 Problems | As a User, I want to be able to enter Problems from Section 1.1 so that I can see their solutions and a step-by-step guide to solving them.
E01.1.2 | Section 1.1 Examples | As a User, I want to be able to review Problems from Section 1.1 so that I can see their solutions and a step-by-step guide to solving them.
E01.2.1 | Section 1.2 Problems | As a User, I want to be able to enter Problems from Section 1.2 so that I can see their solutions and a step-by-step guide to solving them.
E01.2.2 | Section 1.2 Examples | As a User, I want to be able to review Problems from Section 1.2 so that I can see their solutions and a step-by-step guide to solving them.
E03.1.1 | Section 3.1 Problems | As a User, I want to be able to enter Problems from Section 3.1 so that I can see their solutions and a step-by-step guide to solving them.
E03.1.2 | Section 3.1 Examples | As a User, I want to be able to review Problems from Section 3.1 so that I can see their solutions and a step-by-step guide to solving them.
E04.1.1 | Section 4.1 Problems | As a User, I want to be able to enter Problems from Section 4.1 so that I can see their solutions and a step-by-step guide to solving them.
E04.1.2 | Section 4.1 Examples | As a User, I want to be able to review Problems from Section 4.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.1.1 | Section 5.1 Problems | As a User, I want to be able to enter Problems from Section 5.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.1.2 | Section 5.1 Examples | As a User, I want to be able to review Problems from Section 5.1 so that I can see their solutions and a step-by-step guide to solving them.
E05.2.1 | Section 5.2 Problems | As a User, I want to be abe to enter Problems from section 5.2 so that I can see their solutions and a step-by-step guide to solving them.
E05.2.2 | Section 5.2 Examples | As a User, I want to be able to review Problems from section 5.2 so that I can see their solution and a step-by-step guide to solving them
E05.4.1 | Section 5.4 Problems | As a User, I want to be able to enter Problems from Section 5.4 so that I can see their solutions and a step-by-step guide to solving them.
E05.4.2 | Section 5.4 Examples | As a User, I want to be able to review Problems from Section 5.4 so that I can see their solutions and a step-by-step guide to solving them.
E05.5.1 | Section 5.5 Problems | As a User, I want to be able to enter Problems from Section 5.5 so that I can see their solutions and a step-by-step guide to solving them.
E05.5.2 | Section 5.5 Examples | As a User, I want to be able to review Problems from Section 5.5 so that I can see their solutions and a step-by-step guide to solving them.
E05.7.1 | Section 5.7 Problems | As a User, I want to be able to enter Problems from Section 5.7 so that I can see their solutions and a step-by-step guide to solving them.
E05.7.2 | Section 5.7 Examples | As a User, I want to be able to review Problems from Section 5.7 so that I can see their solutions and a step-by-step guide to solving them.
E06.1.1 | Section 6.1 Problems | As a User, I want to be able to enter Problems from Section 6.1 so that I can see their solutions and a step-by-step guide to solving them.
E06.1.2 | Section 6.1 Examples | As a User, I want to be able to review Problems from Section 6.1 so that I can see their solutions and a step-by-step guide to solving them.
E06.2.1 | Section 6.2 Problems | As a User, I want to be able to enter Problems from Section 6.2 so that I can see their solutions and a step-by-step guide to solving them.
E06.2.2 | Section 6.2 Examples | As a User, I want to be able to review Problems from Section 6.2 so that I can see their solutions and a step-by-step guide to solving them.
E07.1.1 | Section 7.1 Problems | As a User, I want to be able to enter Problems from Section 7.1 so that I can see their solutions and a step-by-step guide to solving them.
E07.1.2 | Section 7.1 Examples | As a User, I want to be able to review Problems from Section 7.1 so that I can see their solutions and a step-by-step guide to solving them.
E08.1 | Website User Input | As a User, I want to be able to manually enter logical problems so that I can better study CS 214 and check my work.
E08.2 | Website Bug Reporting | As a User, I want to be able to report problems with the site to the webmaster.
E09.1 | Webmaster Controls | As a Webmaster, I want to be able to review user data such as basic user information, connection time, features used/accessed, and user inputs so that I can monitor website usage.

## User Stories
Parent Epic ID | User Story ID | Title | Description | Assigned to - Primary | Assigned to - Secondary | Sprint Number
E01.1.1 | US01 | Truth Table Construction | Construct Truth Table from wff. Note any tautologies or contradictions. | Sam |  | 1
E01.1.1 | US02 | Tautological Proofing | Convert left side of bioconditional statement to right side in order to verify a tautology. Step-by-step justification required. | Sam |  | 1
E01.1.2 | US03 | Section 1.1 Web-Examples | Lay out practice and example problems from Section 1.1 on web
E01.2.1 | US04 | Justify Proofing Sequence | Jusitfy propositional logic proofing sequence with steps | Sam
E01.2.2 | US05 | Section 1.2 Web-Examples | Lay out practice and example problems from Section 1.2 on web
E03.1.1 | US06 | Section 3.1 Recursive Defintions | Be able to solve 3.1 homework problems on web | Sam |  | 1 | Done
E03.1.2 | US07 | Section 3.1 Web-Examples | Lay out practice and example problems from Section 3.1 on web | Sam
E04.1.1 | US08 | Is statement true given Set definition | User input set definition either in form {x,y,z,...} or {x¦x ∈ N and 1 < x < 50}, tell whether 5 ⊆ A is true or false and why or why not. | Bryce |  | 2
E04.1.1 | US09 | Power Set Computation | Compute and display the power set given a user-entered set. Nested power sets must be able to be worked as well. | Bryce |  | 2
E04.1.1 | US10 | Homework Problem 40b | Is given operation a binary operations on set S? | Bryce
E04.1.1 | US11 | Set Operations (Union, Intersect, Compliment, Subsets, Difference, Cross Product) | Homework problems 47 - 51. | Bryce
E04.1.2 | US12 | Section 4.1 Web-Examples | Lay out practice and example problems from 4.1 on web.
E05.1.1 | US13 | Test Binary relations on S for reflexivity, symmetry, antisymmetry, and transitivity | Problems 11 and 12 from Section 5.1 | Bryce
E05.1.1 | US14 | Find reflexiv, symmetric, and transitive closures given sets and relations | Problems 23 and 24 from Section 5.1 | Bryce
E05.1.1 | US15 | Draw Hasse Diagrams for Partial Orderings | Problem 31 from Section 5.1 | Bryce
E05.1.1 | US16 | for problem 31 name least, minimal, greatest, and max elements | Problem 32 from Section 5.1 | Bryce
E05.1.1 | US17 | partitions, list ordered pairs, equivalence relation | Problem 51a and b | Bryce
E05.1.2 | US18 | Section 5.1 Web-Examples | Lay out practice and example problems from 5.1 on web
E05.2.1 | US19 | Construct PERT charts, compute min time | Construct PERT charts from task table, and compute minimum time | Pierre |  | 1
E05.2.1 | US20 | Create topological Sort for partially ordered set | create algo that can create a tree in an array for partially ordered sets | Pierre |  | 1
E05.2.2 | US21 | Section 5.2 Web-examples | Lay out practice and example problems from 5.2 on the web | Pierre |  | 1
E05.4.1 | US22 | Section 5.4 Web - Examples | Lay out practice and example problems from 5.4 on web | Pierre |  | 1
E05.4.2 | US23 | Solve permutation functions in cycle form | create algo to solve and display exceptions | Pierre |  | 1
E05.4.2 | US24 | composition of permutation cycles /disjoint cycles | get the composition of permuation cycles with disjoint cycles | Pierre |  | 1
E05.5.1 | US25 | Prove, by finding constants, an order of magnitude problem | Problems 3-6 from Section 5.1
E05.5.1 | US26 | Use Master Theorem to determine an order of magnitude expression | Problems 21-26 from Section 5.1
E05.5.2 | US27 | Section 5.5 Web-examples | Lay out practice and example problems from 5.5 on the web.
E05.7.1 | US48 | boolean matrix structure | create Structure to store boolean matrix | Chaz |  | 1
E05.7.1 | US49 | boolean matrix operation | Cross Matrix, AND, OR, ETC | Chaz |  | 1
E05.7.1 | US50 | boolean matrix Input and GUI solver | Render the MAtrix and show the steps taken to solve the matrix | Chaz |  | 1
E06.1.1 | US28 | *6.1* Create an adjacency matrix from a graph | Read edges of a graph and convert it to an adjacency matrix | Chaz |  | 1
E06.1.1 | US29 | Create a graph from an adjacency matrix | Read in a matrix and convert it to an image file of a graph | Chaz |  | 1
E06.1.1 | US30 | Create an adjacency list from a graph | Read edges of a graph and convert it to a list of connections | Chaz |  | 1
E06.1.1 | US31 | Create a graph from an adjacency list | Read in an adjacency list and convert it to an image file of a graph | Chaz |  | 1
E06.1.1 | US32 | Create array-pointer representations from a graph | Read in a graph and create a table of the array-pointer representations | Chaz |  | 1
E06.1.2 | US33 | Section 6.1 Web-Examples | Lay out practice and example problems from 6.1
E06.2.1 | US34 | Section 6.2 Web - Examples | Lay out practice and example problems from 6.2
E06.2.2 | US35 | Expression trees (5-8) | be able to create expression trees from equations
E06.2.2 | US36 | left child right child representation (9-12,15,16) | write/draw left child and right child from binary trees and trees
E06.2.2 | US37 | (preorder, inorder, postorder) traversal (19-24) | write the list of nodes in all forms of traversale
E06.2.2 | US38 | prefix, postfix, infix, expression (25 - 32) | write from any notation into any other notation and evaluate them
US39
US40
US41
US42
US43
US44
US45
US46
US47

## Configuration Items
CI-ID | Short Name | Long description
CI-01
CI-02
CI-03
CI-04
CI-05
CI-06
CI-07
CI-08
CI-09

## Requirements
Parent CI | Requirement ID | Title | Requirement Statement (Shall) | Additonal Information | Assigned to
Rqmt01
Rqmt02
Rqmt03
Rqmt04
Rqmt05
Rqmt06
Rqmt07
Rqmt08
Rqmt09
Rqmt10
Rqmt11
Rqmt12
Rqmt13
Rqmt14
Rqmt15
Rqmt16
Rqmt17
Rqmt18
Rqmt19
Rqmt20
Rqmt21
Rqmt22
Rqmt23
Rqmt24
Rqmt25
Rqmt26
Rqmt27
Rqmt28
Rqmt29
Rqmt30
Rqmt31
Rqmt32
Rqmt33
Rqmt34

## Key Decisions
Key Decision ID
KD01 | Using python as our backend and java script with react for front end
KD02 | We are choosing to use Epics and User Stories
KD03 | Using trello for assigning work
KD04
KD05
KD06
KD07
KD08
KD09
KD10
KD11
KD12

## Schedule
Title | Scheduled Start Date | Actual Start Date | Scheduled Complete Date | Actual Complete Date | Assigned to | Verified by
Team Report Week 1 | 2022-01-11 | 2022-01-11 | 2022-01-16 | 2022-01-16 | ALL | Bryce
Team Report Week 2 | 2022-01-17 | 2022-01-18 | 2022-01-23 | 2022-01-23 | Bryce | Bryce
Team Report Week 3 | 2022-01-24 | 2022-01-24 | 2022-01-30 | 2022-01-30 | ALL | Bryce
Team Report Week 4 |  |  | 2022-02-06
Team Report Week 5 |  |  | 2022-02-13
Team Report Week 6 |  |  | 2022-02-20
Team Report Week 7 |  |  | 2022-02-27
Team Report Week 8 |  |  | 2022-03-06
Team Report Week 9 |  |  | 2022-03-13
Team Report Week 10 |  |  | 2022-03-20
Team Report Week 11 |  |  | 2022-03-27
Team Report Week 12 |  |  | 2022-04-03
Team Report Week 13 |  |  | 2022-04-10
Team Report Week 14 |  |  | 2022-04-17
Team Report Week 15 |  |  | 2022-04-24
Team Report Week 16 |  |  | 2022-05-01
Individual Report Week 1 | 2022-01-11 | 2022-01-11 | 2022-01-16 | 2022-01-16 | ALL | ALL
Individual Report Week 2 | 2022-01-17 | 2022-01-17 | 2022-01-23 | 2022-01-23 | ALL | ALL
Individual Report Week 3 | 2022-01-24 | 2022-01-25 | 2022-01-30 | 2022-01-30 | ALL | ALL
Individual Report Week 4 |  |  | 2022-02-06
Individual Report Week 5 |  |  | 2022-02-13
Individual Report Week 6 |  |  | 2022-02-20
Individual Report Week 7 |  |  | 2022-02-27
Individual Report Week 8 |  |  | 2022-03-06
Individual Report Week 9 |  |  | 2022-03-13
Individual Report Week 10 |  |  | 2022-03-20
Individual Report Week 11 |  |  | 2022-03-27
Individual Report Week 12 |  |  | 2022-04-03
Individual Report Week 13 |  |  | 2022-04-10
Individual Report Week 14 |  |  | 2022-04-17
Individual Report Week 15 |  |  | 2022-04-24
Individual Report Week 16 |  |  | 2022-05-01
SDP Submission |  |  | 2022-01-31
User Stories /Requirements |  |  | 2022-02-14
Architerctural Design |  |  | 2022-03-07
Preliminary GIU Design |  |  | 2022-03-28
Beta Release |  |  | 2022-03-31
Delivery Rev 1.0 |  |  | 2022-03-12
Final delivery |  |  | 2022-04-25
Formulas:
Actual Start Date = [Scheduled Start Date]
Actual Complete Date = [Scheduled Complete Date]
Scheduled Complete Date = [Scheduled Complete Date, row above]+7

## Test Cases
Test Case Number | Requirement(s) | Title | Description | Assigned to: | Status
TC01
TC02
TC03
TC04
TC05
TC06
TC07
TC08
TC09

## Risk Tracking
Risk ID | Risk Title | Likelihood | Impact Level | Risk Score | Mitigation Steps
R-01 | Transition to Full Online | 4 | 3 | 12 | We are organizing the project in such a way that it is doable remotely. Remote technologies are being used (such as discord, github, trello, email, text, etc.)
R-02 | Team Member Fired | 1 | 4 | 4 | Project Schedule is fluid and front-loaded.
R-03 | Team Member Requires Sick Leave | 2 | 2 | 4 | Project Schedule is fluid and front-loaded.
Issue ID | Issue Title | Impact Level | Mitigation Steps
I-01 | Lack of Web-Dev Experience | 2 | Time to research and learn the basics of web development has been scheduled.

## Problem Reports
Number | Title | Date Open | Status | Assigned to: | Verified by: | Date Closed
SPR-01
SPR-02
SPR-03
SPR-04
SPR-05
SPR-06
SPR-07
SPR-08
SPR-09
SPR-10
SPR-11
SPR-12
SPR-13
SPR-14
SPR-15
SPR-16
SPR-17
SPR-18
SPR-19
SPR-20
SPR-21
SPR-22
SPR-23
SPR-24
SPR-25
SPR-26
SPR-27
SPR-28
SPR-29

## Lists
Primary Role | Meeting Role | AI Status | Term Start Date | Term End Date | Test Status | SPR Status | Assignments
Team Lead | Moderator | Open | 2022-01-11 | 2022-04-29 | Not Tested | Open | Sam
Technical Lead | Recorder | Closed-Resolved |  |  | In-Process | In-Work | Bryce
Technical Writer | Present | Closed-Withdrawn |  |  | Tested-Failed | Corrected | Pierre
Test Lead | Absent - Known | Pending |  |  | Tested-Passed | Closed | Chaz
Tools Lead | Absent - Unknown
CM Lead | [6 empty] | ALL
Quality Lead | [6 empty] | TBD
Scrum Master | [6 empty] | NA